## Bugs reported
ID | Title | Severity | Environment | Viewport | Preconditions | Repro steps | Expected behavior | Actual behavior | Evidence | Related
BUG-001 | Complete error message not show when trying to login with empty credential fields | Minor | Testing | Web, Tablet, Mobile | Be in Sauce Labs login page | 1-Leave the username and password fields empty 2-Click Login | An error message will display: "Epic sadface: Username and Password is required" | The error message is "Epic sadface: Username is required", not including the Password field in the message. If only Password field is left empty, the message includes id |  | US-002
BUG-002 | Incorrect product description for Sauce Labs Backpack | Minor | Testing | Web, Tablet, Mobile | Have valid user credentials | 1- Log into Sauce Labs site with credentials mentioned in preconditions 2- Check the product Sauce Labs Backpack description | The description will be: "Carry all the things with the sleek, streamlined Sly Pack that melds uncompromising style with unequaled laptop and tablet protection." | The description is "carry.allTheThings() with the sleek, streamlined Sly Pack that melds uncompromising style with unequaled laptop and tablet protection." |  | US-004
BUG-003 | System redirects to incorrect page after clicking cancel on checkout overview | Minor | Testing | Web, Tablet, Mobile | Have valid user credentials | 1-Go to Login page of Sauce Labs 2-Log i with credentials mentioned in preconditions 3-Select an item on the catalog and add it to the Cart 4-Go to the cart 5-Click checkout 6-Complete the personal information asked in /checkout-step-one.html 7-Click Continue 8-In /checkout-step-two.html page, click Cancel button | The system will redirect the user to the previous page, /checkout-step-one.html | The system redirects the user to the product catalog page (/inventory.html) |  | US-014
BUG-004 | Reset App State does not reset the UI modifications after clicking it | Medium | Testing | Web, Tablet, Mobile | Have valid user credentials | 1-Go to Login page of Sauce Labs 2-Log i with credentials mentioned in preconditions 3-Select one or more items on the catalog and add the to the Cart 4-On the burguer menu icon, click "Reset App State" | Reset clears cart badge and UI modifications without logging out. | Cart badge resets, but products that were added to the cart in step 3 still show the "Remove" button |  | US-011
BUG-005 | Excesive empty space between product description and its price | Minor | Testing | Mobile | Have valid user credentials | 1-Go to Login page of Sauce Labs 2-Log i with credentials mentioned in preconditions 3-Visualize a product of the catalog | The space between the description and price is reasonable | There is excesive empty space between product description and price |  | US-006
BUG-006 | User can make a purchase with empty cart | Medium | Testing | Web, Tablet, Mobile | Have valid user credentials | 1-Go to Login page of Sauce Labs 2-Log in with credentials mentioned in preconditions 3-Go to the cart 4-If there are any items in the cart, remove them until is empty 5-Click checkout | An error message will display, indicating that there are no items to checkout | The system allows the user to complete the whole purchase workflow without items in the cart |  | US-012
BUG-007 | Incorrect product title for Sauce LabsT-Shirt | Minor | Testing | Web, Tablet, Mobile | Have valid user credentials | 1- Log into Sauce Labs site with credentials mentioned in preconditions 2- Check the product Sauce Labs T-Shirt title | The title o the product will be "Sauce Labs T-Shirt (Red) | The product title is "Test.allTheThings() T-Shirt (Red)" |  | US-004